## Config v3 (hidden)
Members | Priorities | Plants | Task Types | Milestones | Milestone Progress % | Tasks_Chaitanya | Tasks_Nagesh | Tasks_Piyush | Tasks_Harshala | Tasks_Shruti
Chaitanya | High | Anjangoan | New Site Integration | Not Started | 0%
Nagesh | Medium | Sirmour | Bug Fix | Development | 20%
Piyush | Low | CME | Cloud Deployment | Local Testing | 40%
Harshala |  | GSNP | Schedule Logic | Testing Repo | 60%
Shruti |  | Kasipet | Forecast | Testing Cloud | 80%
|  | Kothagudem | Metered Data | Production Repo | 90%
|  | OSEPL | Weather Ingestion | Production Cloud | 95%
|  | Other | UI Change | Monitoring | 100%
|  |  | Testing | Completed | 100%
|  |  | Monitoring | Blocked

## Config v4 (hidden)
Members | Priority | Task Status | Milestone Values
Chaitanya | High | Not Started | Yes
Nagesh | Low | In Progress | No
Piyush |  | In Progress Delayed
Harshala |  | Completed
Shruti

## Task Registry v4
Task ID | Task Name | Priority | Assigned Members | Start Date | Expected Completion Date | Task Progress % | Task Status | Actual Completion Date | Completion Timing | Local Code Status | Testing cloud env code status | Production cloud env code status | Testing GitHub Migration | Testing GitHub Commit Message | Testing Cloud Migration | Production GitHub Migration | Production GitHub Commit Message | Production Cloud Migration | Members Worked | Work History Log | Remarks
T-001 | Implement the email scheduler | High | Nagesh, Harshala | 2026-06-06 | 2026-06-09 | 100% | Completed | 2026-06-07 | Early by 2 days | Completed | Completed | Completed | Yes | 2026-06-07 - Harshala - Emailscheduler | Yes | Yes | 2026-06-07 - Harshala - EmailechedulerDone | Yes | Nagesh, Harshala | 2026-06-06 - Nagesh - In Progress 2026-06-07 - Harshala - Completed | 2026-06-06 - Harshala - Need to complete the local env developlemnt and needed to test 2026-06-07 - Chaitanya - Need to test
Formulas:
Actual Completion Date = IF([Task Status]="Completed", XLOOKUP([Task Name], 'Daily Work Logs v4'!$C2:C1001, 'Daily Work Logs v4'!$A2:A1001, "", 0, -1), "")

## Daily Work Logs v4
Date | Member | Task Selected | Priority | Start Date | Expected Completion Date | Previous Progress % | Current Task Status | Changes Done Today | Local Code Status | Testing cloud env code status | Production cloud env code status | Testing GitHub Migration | Testing GitHub Commit Message | Testing Cloud Migration | Production GitHub Migration | Production GitHub Commit Message | Production Cloud Migration | Updated Progress % | Updated Task Status | Reviewed By | Remarks
2026-06-06 | Nagesh | Implement the email scheduler | High | 2026-06-06 | 2026-06-09 | 0% | Not Started | Migrated to the production env | Development | Not Started | Not Started | No |  | No | No |  | No | 10% | In Progress | Harshala | Need to complete the local env developlemnt and needed to test
2026-06-07 | Harshala | Implement the email scheduler | High | 2026-06-06 | 2026-06-09 | 10% | In Progress | Migrated the email scheduler to the production env | Completed | Completed | Completed | Yes | Emailscheduler | Yes | Yes | EmailechedulerDone | Yes | 100% | Completed | Chaitanya | Need to test
Formulas:
Start Date = IF([Task Selected]="", "", IFERROR(VLOOKUP([Task Selected], 'Task Registry v4'!B:G, 4, FALSE), ""))
Expected Completion Date = IF([Task Selected]="", "", IFERROR(VLOOKUP([Task Selected], 'Task Registry v4'!B:G, 5, FALSE), ""))

## Dropdown_Helper (hidden)
Implement the email scheduler
Implement the email scheduler

## Dashboard
Total Tasks | High Priority Tasks | Low Priority Tasks | Completed Tasks
1 | 1 | 0 | 1
FALSE | FALSE | FALSE | FALSE